MedCare

Implementation Plan & Task Tracker

Version 1.0  ·  March 2026  ·  Phase 1 (MVP)

| Project | MedCare — Automated Pill Dispensing System |
| --- | --- |
| Document | Implementation Plan & Task Tracker |
| Phase | Phase 1 — MVP |
| Sprint Length | 2 weeks per sprint |
| Total Sprints | 6 sprints (~12 weeks) |
| Target Launch | Q2 2026 |
| Team | Engineering + Hardware + Product |

# 📋  1. Overview & Sprint Plan

This document tracks all implementation tasks for MedCare Phase 1 (MVP). Tasks are organized by domain and assigned to sprints. Update the Status column as work progresses. Each sprint is 2 weeks.

## Sprint Schedule

| Sprint | Dates | Focus | Milestone |
| --- | --- | --- | --- |
| S1 | Wk 1–2 | Project setup, repo structure, CI/CD, database schema, hardware procurement | Infra ready |
| S2 | Wk 3–4 | Supabase schema complete, Elysia.js API core endpoints, Raspberry Pi + Moonraker basic integration | API running |
| S3 | Wk 5–6 | Touchscreen UI (all 4 steps), dispense workflow end-to-end, hardware dispense tested | Dispenser works |
| S4 | Wk 7–8 | Next.js web app: resident profiles, digital Med Sheet, real-time sync | Web app live |
| S5 | Wk 9–10 | Stock tracking, LINE notifications, dispense history, audit log | Alerts live |
| S6 | Wk 11–12 | QA, pilot testing at facility, bug fixes, staff training, production deployment | MVP launch |

## Overall Progress

Phase 1 Tasks     ░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░  0/72 (0%)

Hardware          ░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░  0/8 (0%)

Backend / API     ░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░  0/14 (0%)

Database          ░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░  0/12 (0%)

Touchscreen UI    ░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░  0/16 (0%)

Web App           ░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░  0/14 (0%)

QA & Launch       ░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░  0/8 (0%)

# ⚙️  2. Hardware & Physical Setup

Physical machine construction and embedded software for the Raspberry Pi dispenser unit.

🔧 Sprint 1–2 Procurement & base setup

| ID | Task | Owner | Sprint | Status |
| --- | --- | --- | --- | --- |
| H-01 | ☐ Procure Raspberry Pi 4 (4GB), power supply, SD card (64GB) | Hardware Lead | S1 | ○ Not Started |
| H-02 | ☐ Procure 7-inch DSI touchscreen display (1024×600) | Hardware Lead | S1 | ○ Not Started |
| H-03 | ☐ Procure stepper motors, motor drivers (A4988 or TMC2209) | Hardware Lead | S1 | ○ Not Started |
| H-04 | ☐ Design and 3D-print pill channel frame (6–8 channels) | Hardware Lead | S2 | ○ Not Started |
| H-05 | ☐ Assemble pill channel + collection cup mechanism | Hardware Lead | S2 | ○ Not Started |
| H-06 | ☐ Install Raspberry Pi OS, configure kiosk mode for touchscreen | Backend Dev | S2 | ○ Not Started |
| H-07 | ☐ Install and configure Moonraker API on Raspberry Pi | Backend Dev | S2 | ○ Not Started |
| H-08 | ☐ Test single-channel dispense: command → motor → pill drop | Hardware Lead | S3 | ○ Not Started |

# 🗄️  3. Database & Backend Infrastructure

Supabase schema design, Elysia.js API setup, and core backend infrastructure.

🗃️ Sprint 1–2 Schema & API core

### 3.1 Supabase Schema

| ID | Task | Owner | Sprint | Status |
| --- | --- | --- | --- | --- |
| DB-01 | ☐ Create `residents` table (id, name, room, ward, photo_url, flags, allergies) | Backend Dev | S1 | ○ Not Started |
| DB-02 | ☐ Create `medications` table (id, name, form, dosage_unit, notes) | Backend Dev | S1 | ○ Not Started |
| DB-03 | ☐ Create `resident_medications` table (resident_id, medication_id, dose, schedule array) | Backend Dev | S1 | ○ Not Started |
| DB-04 | ☐ Create `dispense_events` table (id, resident_id, meal, medications_json, staff_id, timestamp) | Backend Dev | S1 | ○ Not Started |
| DB-05 | ☐ Create `stock` table (medication_id, quantity, threshold_warn, threshold_critical, updated_at) | Backend Dev | S2 | ○ Not Started |
| DB-06 | ☐ Create `users` table and roles (admin, nurse, caregiver, family) | Backend Dev | S1 | ○ Not Started |
| DB-07 | ☐ Enable Supabase Realtime on `resident_medications` and `stock` tables | Backend Dev | S2 | ○ Not Started |
| DB-08 | ☐ Write seed data: 5 sample residents with full medication schedules | Backend Dev | S2 | ○ Not Started |

### 3.2 Elysia.js API Endpoints

| ID | Task | Owner | Sprint | Status |
| --- | --- | --- | --- | --- |
| API-01 | ☐ GET /residents — list all residents with status (pending/done) | Backend Dev | S2 | ○ Not Started |
| API-02 | ☐ GET /residents/:id — full resident profile + medication schedule | Backend Dev | S2 | ○ Not Started |
| API-03 | ☐ POST /residents — create new resident | Backend Dev | S2 | ○ Not Started |
| API-04 | ☐ PATCH /residents/:id — update resident profile or medication | Backend Dev | S2 | ○ Not Started |
| API-05 | ☐ POST /dispense — trigger dispense command, log event to DB | Backend Dev | S3 | ○ Not Started |
| API-06 | ☐ GET /dispense/history — list events with filters (date, resident) | Backend Dev | S3 | ○ Not Started |
| API-07 | ☐ GET /stock — current stock levels with alert flags | Backend Dev | S3 | ○ Not Started |
| API-08 | ☐ PATCH /stock/:id — update stock quantity | Backend Dev | S3 | ○ Not Started |
| API-09 | ☐ POST /notify/line — send LINE message to family for stock alert | Backend Dev | S5 | ○ Not Started |
| API-10 | ☐ Implement JWT auth middleware for all endpoints | Backend Dev | S2 | ○ Not Started |
| API-11 | ☐ Set up rate limiting and CORS configuration | Backend Dev | S2 | ○ Not Started |
| API-12 | ☐ Moonraker bridge: translate POST /dispense → Moonraker G-code command | Backend Dev | S3 | ○ Not Started |

# 📱  4. Touchscreen Application (Dispenser UI)

HTML/CSS/JS app running in kiosk mode on the 7-inch Raspberry Pi touchscreen (1024×600 landscape). All buttons must be ≥ 48px tall. Thai language throughout.

🖥️ Sprint 3 Full 4-step workflow

### Step 1 — Select Resident

| ID | Task | Owner | Sprint | Status |
| --- | --- | --- | --- | --- |
| UI-01 | ☐ Build resident grid layout: 5-per-row cards, avatar, name, room, medication count | Frontend Dev | S3 | ○ Not Started |
| UI-02 | ☐ Implement weekly progress counter sidebar (X of 54 done) | Frontend Dev | S3 | ○ Not Started |
| UI-03 | ☐ Mark completed residents as greyed-out with ✓ badge | Frontend Dev | S3 | ○ Not Started |
| UI-04 | ☐ Show urgent indicator (red dot) for residents with low-stock warning | Frontend Dev | S3 | ○ Not Started |
| UI-05 | ☐ Stock summary sidebar: critical / warning / normal counts | Frontend Dev | S3 | ○ Not Started |
| UI-06 | ☐ Fetch resident list from API; cache locally for offline use | Frontend Dev | S3 | ○ Not Started |

### Step 2 — Medication Loading List

| ID | Task | Owner | Sprint | Status |
| --- | --- | --- | --- | --- |
| UI-07 | ☐ Display resident hero card: avatar, name, room, stats (types / total tablets / meals) | Frontend Dev | S3 | ○ Not Started |
| UI-08 | ☐ Render medication list rows with: drug name, dosage, weekly total, meal chips | Frontend Dev | S3 | ○ Not Started |
| UI-09 | ☐ Large (56×56px) tick button per medication row; row highlights green on tick | Frontend Dev | S3 | ○ Not Started |
| UI-10 | ☐ Show special flags inline: 🔴 Crush, ⏰ Timed dose, 💧 Liquid | Frontend Dev | S3 | ○ Not Started |
| UI-11 | ☐ Show stock warning panel if any medication is low | Frontend Dev | S3 | ○ Not Started |
| UI-12 | ☐ "Start Dispense" button — enabled only when all medications are ticked | Frontend Dev | S3 | ○ Not Started |

### Step 3 — Dispense Per Meal

| ID | Task | Owner | Sprint | Status |
| --- | --- | --- | --- | --- |
| UI-13 | ☐ Sidebar: meal progress list (icon + name + count) with done/active/upcoming states | Frontend Dev | S3 | ○ Not Started |
| UI-14 | ☐ Current meal header: large icon + meal name + item count badge | Frontend Dev | S3 | ○ Not Started |
| UI-15 | ☐ Medication rows with animated states: idle → dispensing (yellow) → done (green) | Frontend Dev | S3 | ○ Not Started |
| UI-16 | ☐ Tray bar: show 💊 emoji accumulating + running pill count | Frontend Dev | S3 | ○ Not Started |
| UI-17 | ☐ "Transfer to box" collect panel: appears after dispense completes, shows slot label | Frontend Dev | S3 | ○ Not Started |
| UI-18 | ☐ "Done — next meal" button triggers API dispense for next meal | Frontend Dev | S3 | ○ Not Started |
| UI-19 | ☐ Send POST /dispense to API when each meal dispense starts | Frontend Dev | S3 | ○ Not Started |
| UI-20 | ☐ Handle dispense API error: show retry prompt, do not advance to next meal | Frontend Dev | S3 | ○ Not Started |

### Step 4 — Completion & Navigation

| ID | Task | Owner | Sprint | Status |
| --- | --- | --- | --- | --- |
| UI-21 | ☐ Completion screen: animated icon, resident name, total pills, days, stat grid | Frontend Dev | S3 | ○ Not Started |
| UI-22 | ☐ "Next Resident" button: marks resident done in local state, returns to Step 1 | Frontend Dev | S3 | ○ Not Started |
| UI-23 | ☐ Step indicator bar (1 → 2 → 3 → 4) shown in topbar throughout flow | Frontend Dev | S3 | ○ Not Started |
| UI-24 | ☐ Offline mode: detect network loss, show warning banner, queue events for sync | Frontend Dev | S4 | ○ Not Started |
| UI-25 | ☐ Auto-launch kiosk browser on Raspberry Pi boot (chromium --kiosk) | Backend Dev | S3 | ○ Not Started |

# 🌐  5. Web Application (Next.js)

Admin and nurse interface for managing residents, medications, stock, and dispense history. Accessible from any browser.

🏠 Sprint 4 Core resident & medication management

### 5.1 Authentication & Layout

| ID | Task | Owner | Sprint | Status |
| --- | --- | --- | --- | --- |
| WA-01 | ☐ Set up Next.js project with TypeScript, Tailwind CSS, Supabase client | Frontend Dev | S1 | ○ Not Started |
| WA-02 | ☐ Implement Supabase Auth: login page, session management, protected routes | Frontend Dev | S2 | ○ Not Started |
| WA-03 | ☐ Role-based access control: nurse sees all, family sees only their resident | Frontend Dev | S2 | ○ Not Started |
| WA-04 | ☐ App shell: sidebar navigation, topbar with user info and logout | Frontend Dev | S2 | ○ Not Started |

### 5.2 Resident Management

| ID | Task | Owner | Sprint | Status |
| --- | --- | --- | --- | --- |
| WA-05 | ☐ Resident list page: search, filter by ward, show dispense status | Frontend Dev | S4 | ○ Not Started |
| WA-06 | ☐ Resident detail page: 4 tabs — Medications, Profile, Vitals, History | Frontend Dev | S4 | ○ Not Started |
| WA-07 | ☐ Create/edit resident form: personal info, room, allergies, contact | Frontend Dev | S4 | ○ Not Started |
| WA-08 | ☐ Special flags UI: toggle for crush meds, liquid meds, requires assistance | Frontend Dev | S4 | ○ Not Started |

### 5.3 Digital Med Sheet

| ID | Task | Owner | Sprint | Status |
| --- | --- | --- | --- | --- |
| WA-09 | ☐ Med Sheet view: table of all medications per resident with meal columns | Frontend Dev | S4 | ○ Not Started |
| WA-10 | ☐ Add/edit/remove medication from a resident's schedule | Frontend Dev | S4 | ○ Not Started |
| WA-11 | ☐ Change highlighting: flag medications added/changed in the last 48h | Frontend Dev | S4 | ○ Not Started |
| WA-12 | ☐ Realtime sync: Med Sheet updates instantly on touchscreen via Supabase Realtime | Frontend Dev | S4 | ○ Not Started |

### 5.4 Stock Management

| ID | Task | Owner | Sprint | Status |
| --- | --- | --- | --- | --- |
| WA-13 | ☐ Stock dashboard: list all medications with current quantity and status badge | Frontend Dev | S5 | ○ Not Started |
| WA-14 | ☐ Inline edit stock quantity after replenishment | Frontend Dev | S5 | ○ Not Started |
| WA-15 | ☐ Auto-calculate estimated run-out date based on daily consumption | Frontend Dev | S5 | ○ Not Started |
| WA-16 | ☐ Stock request tracker: log family notification → acknowledged → received | Frontend Dev | S5 | ○ Not Started |

### 5.5 Dispense History & Reports

| ID | Task | Owner | Sprint | Status |
| --- | --- | --- | --- | --- |
| WA-17 | ☐ Dispense history page: filterable by date, resident, staff member | Frontend Dev | S5 | ○ Not Started |
| WA-18 | ☐ Dispense event detail: which medications, quantities, timestamp, staff | Frontend Dev | S5 | ○ Not Started |
| WA-19 | ☐ Export dispense history to PDF for compliance records | Frontend Dev | S5 | ○ Not Started |

# 🔔  6. Notifications & Integrations

📲 Sprint 5 LINE alerts and external integrations

| ID | Task | Owner | Sprint | Status |
| --- | --- | --- | --- | --- |
| NT-01 | ☐ Register LINE Messaging API channel for the facility | Backend Dev | S5 | ○ Not Started |
| NT-02 | ☐ Trigger LINE message when stock reaches critical threshold (7 days) | Backend Dev | S5 | ○ Not Started |
| NT-03 | ☐ Trigger LINE message when stock reaches warning threshold (14 days) | Backend Dev | S5 | ○ Not Started |
| NT-04 | ☐ Weekly dispense summary LINE message to head nurse every Sunday | Backend Dev | S5 | ○ Not Started |
| NT-05 | ☐ Store LINE user IDs per family member in Supabase, linked to resident | Backend Dev | S5 | ○ Not Started |

# 🚀  7. QA, Testing & Launch

🧪 Sprint 6 Testing, pilot, and production deployment

### 7.1 Testing

| ID | Task | Owner | Sprint | Status |
| --- | --- | --- | --- | --- |
| QA-01 | ☐ Unit tests for all Elysia.js API endpoints (happy path + error cases) | Backend Dev | S5 | ○ Not Started |
| QA-02 | ☐ Integration test: full dispense workflow (API → Moonraker → motor → sensor) | Hardware Lead | S5 | ○ Not Started |
| QA-03 | ☐ Touchscreen UI: manual test all 4 steps with real resident data | Frontend Dev | S5 | ○ Not Started |
| QA-04 | ☐ Offline mode test: disconnect network mid-dispense and verify graceful fallback | Frontend Dev | S6 | ○ Not Started |
| QA-05 | ☐ Stock alert test: reduce quantity below threshold and verify LINE notification fires | Backend Dev | S6 | ○ Not Started |
| QA-06 | ☐ Load test: simulate 10 concurrent web app users | Backend Dev | S6 | ○ Not Started |

### 7.2 Pilot

| ID | Task | Owner | Sprint | Status |
| --- | --- | --- | --- | --- |
| QA-07 | ☐ Identify 3–5 pilot residents at Saensuk facility for initial trial | Product | S6 | ○ Not Started |
| QA-08 | ☐ Train Khun Bus (head nurse) on web app: Med Sheet editing, stock updates | Product | S6 | ○ Not Started |
| QA-09 | ☐ Train 2 caregivers on touchscreen: run full weekly fill for 3 residents | Product | S6 | ○ Not Started |
| QA-10 | ☐ Observe pilot session and document pain points for backlog | Product | S6 | ○ Not Started |
| QA-11 | ☐ Collect feedback: time savings, errors caught, ease of use | Product | S6 | ○ Not Started |

### 7.3 Production Deployment

| ID | Task | Owner | Sprint | Status |
| --- | --- | --- | --- | --- |
| QA-12 | ☐ Set up production Supabase project (separate from dev) | Backend Dev | S6 | ○ Not Started |
| QA-13 | ☐ Deploy Next.js web app to Vercel (or facility server) | Backend Dev | S6 | ○ Not Started |
| QA-14 | ☐ Deploy Elysia.js API to production server | Backend Dev | S6 | ○ Not Started |
| QA-15 | ☐ Flash production SD card for Raspberry Pi, set up auto-updates | Hardware Lead | S6 | ○ Not Started |
| QA-16 | ☐ Run final end-to-end smoke test in production environment | All | S6 | ○ Not Started |
| QA-17 | ☐ Document runbook: how to restart system, reset dispenser, handle jams | Backend Dev | S6 | ○ Not Started |

# 📌  8. Backlog — Phase 2 (Not in Scope)

The following features are out of scope for Phase 1 and are deferred to Phase 2.

| ID | Feature | Category | Priority |
| --- | --- | --- | --- |
| P2-01 | OCR prescription scanning: auto-populate Med Sheet by scanning medication packaging | AI / Automation | High |
| P2-02 | Multi-channel dispenser: run 2+ channels in parallel to reduce fill time | Hardware | High |
| P2-03 | Drug interaction detection: flag combinations that may be harmful | Safety | High |
| P2-04 | Shift handover module: auto-generated PDF summary for outgoing nurse | Operations | Medium |
| P2-05 | Family portal: web dashboard for relatives to see medication schedule & history | Product | Medium |
| P2-06 | Vital signs logging: BP, glucose, temperature tracking per resident | Clinical | Medium |
| P2-07 | Predictive stock reordering: ML model suggests reorder quantities and timing | AI / Automation | Low |
| P2-08 | Multi-facility support: manage multiple care homes from one platform | Scale | Low |

# 👥  9. Team & Responsibilities

| Role | Owner | Owns |
| --- | --- | --- |
| Product / PM | Mooham | PRD, sprint planning, stakeholder comms, pilot coordination |
| Backend Dev | TBD | Elysia.js API, Supabase schema, Moonraker bridge, LINE integration |
| Frontend Dev | TBD | Next.js web app, Touchscreen HTML/JS app |
| Hardware Lead | TBD | Raspberry Pi, stepper motors, pill channel design, Moonraker config |
| QA | Mooham + Team | Test plans, pilot session, user feedback collection |
| Head Nurse (Client) | Khun Bus | Requirements, UAT, staff training lead at facility |